## Sheet1
TASK | START DATE | DAYS TO COMPLETE
REQUIREMENT GATHERING | 2021-09-03 | 8
UI-HOME | 2021-09-11 | 8
UI-ADMIN | 2021-09-19 | 8
DATA MODEL CREATION | 2021-09-27 | 10
UI-SELLER | 2021-10-07 | 8
DATABASE SELLER DATA LINKING | 2021-10-15 | 4
DATABASE SELLER ORDERS, PRODUCT INFO & AVAILABILITY UPDATION IN THE BACKEND | 2021-10-19 | 12
UI-USER | 2021-11-01 | 8
DATABASE USER DATA LINKING | 2021-11-07 | 4
DATABASE USER ORDERS DATA LINKING | 2021-11-12 | 5
TESTING | 2021-11-17 | 5
BUG FIXING-RISK MANAGEMENT | 2021-11-22 | 5
RE-EVALUATION | 2021-11-27 | 3
PRESENTATION & FINAL DOCUMENTATION | 2021-11-30 | 4